## Compliance Calendar
Task | Owner | Start | Due | Legal Basis | Priority | Status | Notes
Finalize 5 Day22 deliverables | Founder | 2026-05-08 | 2026-05-08 | Day22 submission | High | Done | Submitted to repo
Remove level-C claims from landing/deck | Founder + Marketing | 2026-05-09 | 2026-05-11 | BLHS Art.198 risk control | High | Planned | Use marketing_claims_audit.md
Implement founder marketing approval gate | Founder | 2026-05-09 | 2026-05-16 | BLHS Art.198 prevention | High | Planned | No publish without sign-off
Build data deletion self-service flow | Product + Eng | 2026-05-12 | 2026-05-24 | PDPL compliance | High | Planned | Audit log required
Create vendor abuse monitoring rulebook | Founder + Ops | 2026-05-12 | 2026-05-24 | BLHS Art.324 prevention | High | Planned | Escalation in 24h
Prepare CTIA dossier draft | Founder + Legal advisor | 2026-05-15 | 2026-06-10 | PDPL Art.30 | Critical | Planned | Cross-border transfer mapping
Submit CTIA package | Founder | 2026-06-11 | 2026-06-15 | PDPL Art.30 | Critical | Planned | Track submission evidence
Quarterly legal review | Founder | 2026-06-20 | 2026-06-20 | AI Law + PDPL ongoing | Medium | Planned | Repeat every quarter
Regulatory milestone reminder: EU AI Act high-risk | Founder | 2026-07-02 | 2026-08-02 | EU AI Act | Medium | Planned | Pre-check if EU users appear
Regulatory milestone reminder: grace period end | Founder | 2027-01-01 | 2027-03-01 | VN AI law timeline | Medium | Planned | Final readiness review